## Jira Export Excel CSV (filter f
Date Worked On | Sprint | Issue key | Summary | Hours Log | Status
2025-03-30 | Sprint 7 - Auto Email & UI | SCRUM-54 | Progress Report #4 | 1 | Done
2025-03-28 | Sprint 7 - Auto Email & UI | SCRUM-53 | Retry Production Environment Deployment | 6 | Done
2025-03-26 | Sprint 7 - Auto Email & UI | SCRUM-58 | UI Enhancement 2 | 1.5 | Done
2025-03-26 | Sprint 7 - Auto Email & UI | SCRUM-29 | Store Frequently Asked Questions in MongoDB | 3 | Done
2025-03-25 | Sprint 7 - Auto Email & UI | SCRUM-55 | UI Enhancement 1 | 4 | Done
2025-03-24 | Sprint 7 - Auto Email & UI | SCRUM-52 | Automate Email Reminders | 2 | Done
2025-03-18 | Sprint 6 - Prod Deployment | SCRUM-49 | Deploy FurBot to Railway 3 | 6 | Done
2025-03-17 | Sprint 6 - Prod Deployment | SCRUM-48 | Deploy FurBot to Railway 2 | 4 | Done
2025-03-12 | Sprint 6 - Prod Deployment | SCRUM-47 | Test and Debug - March 12 | 4 | Done
2025-03-12 | Sprint 6 - Prod Deployment | SCRUM-46 | Deploy FurBot to Railway 1 | 4 | Done
2025-03-11 | Sprint 6 - Prod Deployment | SCRUM-45 | Sign up with Railway | 2 | Done
2025-03-10 | Sprint 5 - Chatbot Integration | SCRUM-44 | Creating Progress Report #2 | 2 | Done
2025-03-06 | Sprint 5 - Chatbot Integration | SCRUM-40 | Integrate Yelp with Backend API - March 6 | 1 | Done
2025-03-06 | Sprint 5 - Chatbot Integration | SCRUM-39 | Integrate Yelp with Chatbot UI - March 6 | 1 | Done
2025-03-05 | Sprint 5 - Chatbot Integration | SCRUM-38 | Integrate Yelp with Backend API - March 5 | 1 | Done
2025-03-05 | Sprint 5 - Chatbot Integration | SCRUM-37 | Integrate Yelp with Chatbot UI - March 5 | 2 | Done
2025-03-05 | Sprint 5 - Chatbot Integration | SCRUM-32 | Implement Basic Conversation Flow | 1 | Done
2025-03-04 | Sprint 5 - Chatbot Integration | SCRUM-36 | Integrate Yelp with Chatbot UI - March 4 | 2 | Done
2025-03-04 | Sprint 5 - Chatbot Integration | SCRUM-35 | Integrate Yelp with Backend API - March 4 | 2 | Done
2025-03-04 | Sprint 5 - Chatbot Integration | SCRUM-30 | Create initial Chatbot UI | 1 | Done
2025-03-04 | Sprint 5 - Chatbot Integration | SCRUM-28 | Yelp Registration and Initial Set up | 1 | Done
2025-03-03 | Sprint 5 - Chatbot Integration | SCRUM-34 | Integrate Yelp with Chatbot UI - March 3 | 1 | Done
2025-03-03 | Sprint 5 - Chatbot Integration | SCRUM-31 | Integrate Yelp with Backend API - March 3 | 1 | Done
2025-02-26 | Sprint 5 - Chatbot Integration | SCRUM-27 | Implement Basic Chatbot Logic | 5 | Done
2025-02-20 | Sprint 5 - Chatbot Integration | SCRUM-33 | Midterm Report and Video | 5 | Done
2025-02-19 | Sprint 5 - Chatbot Integration | SCRUM-26 | Create API Endpoint for Chatbot (/chatbot) and Simple UI Integration | 5 | Done
2025-02-18 | Sprint 4 - Building Initial UI | SCRUM-25 | UI testing & debugging | 6 | Done
2025-02-18 | Sprint 4 - Building Initial UI | SCRUM-23 | API integration for authentication & pet management | 3 | Done
2025-02-17 | Sprint 4 - Building Initial UI | SCRUM-24 | User session handling (store token & authentication state) | 4 | Done
2025-02-17 | Sprint 4 - Building Initial UI | SCRUM-22 | Basic UI for Adding & Viewing Pets | 2 | Done
2025-02-17 | Sprint 4 - Building Initial UI | SCRUM-21 | Functional UI for Login & Sign-Up | 2 | Done
2025-02-11 | Sprint 3 - Backend Setup | SCRUM-20 | Set up Job Scheduler to automate the email reminders | 3 | Done
2025-02-09 | Sprint 3 - Backend Setup | SCRUM-17 | Set up Reminders | 3 | Done
2025-02-09 | Sprint 3 - Backend Setup | SCRUM-16 | Create end points for pet profiles | 2 | Done
2025-02-09 | Sprint 3 - Backend Setup | SCRUM-15 | Set up MongoDB for Pet Profiles | 1 | Done
2025-02-06 | Sprint 4 - Building Initial UI | SCRUM-18 | Progress Report #1 | 2 | Done
2025-02-06 | Sprint 2 - Set Up the Backend | SCRUM-14 | Test API | 1 | Done
2025-02-06 | Sprint 2 - Set Up the Backend | SCRUM-12 | Build User Authentication API | 3 | Done
2025-02-05 | Sprint 2 - Set Up the Backend | SCRUM-11 | Set Up MongoDB | 1 | Done
2025-02-05 | Sprint 2 - Set Up the Backend | SCRUM-10 | Install Dependencies | 1 | Done
2025-02-05 | Sprint 2 - Set Up the Backend | SCRUM-9 | Set Up Python and Virtual Environment | 1 | Done
2025-02-05 | Sprint 2 - Set Up the Backend | SCRUM-8 | Create the Folder Structure in the Implementation folder | 1 | Done
2025-01-25 | Sprint 1 - FurBot Setup | SCRUM-1 | Draft Project Proposal | 6 | Done
2025-01-19 | Sprint 1 - FurBot Setup | SCRUM-6 | Set Up Project Repository | 1 | Done
2025-01-19 | Sprint 1 - FurBot Setup | SCRUM-2 | Set Up JIRA for Project Management | 2 | Done
2025-01-18 | Sprint 1 - FurBot Setup | SCRUM-13 | Research a topic for the project proposal | 2 | Done
2025-01-18 | Sprint 1 - FurBot Setup | SCRUM-7 | Research and Identify Technologies for FurBot | 2 | Done