## Jira Export Excel CSV (filter f
Date Started | Issue key | Summary | Hours Spent | Status | Sprint
2025-02-19 | SCRUM-26 | Create API Endpoint for Chatbot (/chatbot) and Simple UI Integration | 5 | Done | Sprint 5 - Chatbot Integration
2025-02-18 | SCRUM-25 | UI testing & debugging | 8 | Done | Sprint 4 - Building Initial UI
2025-02-18 | SCRUM-23 | API integration for authentication & pet management | 3 | Done | Sprint 4 - Building Initial UI
2025-02-17 | SCRUM-24 | User session handling (store token & authentication state) | 4 | Done | Sprint 4 - Building Initial UI
2025-02-17 | SCRUM-22 | Basic UI for Adding & Viewing Pets | 2 | Done | Sprint 4 - Building Initial UI
2025-02-17 | SCRUM-21 | Functional UI for Login & Sign-Up | 2 | Done | Sprint 4 - Building Initial UI
2025-02-11 | SCRUM-20 | Set up Job Scheduler to automate the email reminders | 3 | Done | Sprint 3 - Backend Setup
2025-02-09 | SCRUM-17 | Set up Reminders | 3 | Done | Sprint 3 - Backend Setup
2025-02-09 | SCRUM-16 | Create end points for pet profiles | 2 | Done | Sprint 3 - Backend Setup
2025-02-09 | SCRUM-15 | Set up MongoDB for Pet Profiles | 1 | Done | Sprint 3 - Backend Setup
2025-02-06 | SCRUM-18 | Progress Report #1 | 2 | Done | Sprint 4 - Building Initial UI
2025-02-06 | SCRUM-14 | Test API | 1 | Done | Sprint 2 - Set Up the Backend
2025-02-06 | SCRUM-12 | Build User Authentication API | 3 | Done | Sprint 2 - Set Up the Backend
2025-02-05 | SCRUM-11 | Set Up MongoDB | 1 | Done | Sprint 2 - Set Up the Backend
2025-02-05 | SCRUM-10 | Install Dependencies | 1 | Done | Sprint 2 - Set Up the Backend
2025-02-05 | SCRUM-9 | Set Up Python and Virtual Environment | 1 | Done | Sprint 2 - Set Up the Backend
2025-02-05 | SCRUM-8 | Create the Folder Structure in the Implementation folder | 1 | Done | Sprint 2 - Set Up the Backend
2025-01-25 | SCRUM-1 | Draft Project Proposal | 6 | Done | Sprint 1 - FurBot Setup
2025-01-19 | SCRUM-6 | Set Up Project Repository | 1 | Done | Sprint 1 - FurBot Setup
2025-01-19 | SCRUM-2 | Set Up JIRA for Project Management | 2 | Done | Sprint 1 - FurBot Setup
2025-01-18 | SCRUM-13 | Research a topic for the project proposal | 2 | Done | Sprint 1 - FurBot Setup
2025-01-18 | SCRUM-7 | Research and Identify Technologies for FurBot | 2 | Done | Sprint 1 - FurBot Setup