## Jira Export Excel CSV (filter f
Date Worked On | Issue key | Summary | Number of Hours | Sprint
2025-01-18 | SCRUM-13 | Research a topic for the project proposal | 2 | Sprint 1 - FurBot Setup
2025-01-18 | SCRUM-7 | Research and Identify Technologies for FurBot | 2 | Sprint 1 - FurBot Setup
2025-01-19 | SCRUM-6 | Set Up Project Repository | 1 | Sprint 1 - FurBot Setup
2025-01-19 | SCRUM-2 | Set Up JIRA for Project Management | 2 | Sprint 1 - FurBot Setup
2025-01-25 | SCRUM-1 | Draft Project Proposal | 6 | Sprint 1 - FurBot Setup
2025-02-06 | SCRUM-14 | Test API | 1 | Sprint 2 - Set Up the Backend
2025-02-06 | SCRUM-12 | Build User Authentication API | 3 | Sprint 2 - Set Up the Backend
2025-02-05 | SCRUM-11 | Set Up MongoDB | 1 | Sprint 2 - Set Up the Backend
2025-02-05 | SCRUM-10 | Install Dependencies | 1 | Sprint 2 - Set Up the Backend
2025-02-05 | SCRUM-9 | Set Up Python and Virtual Environment | 1 | Sprint 2 - Set Up the Backend
2025-02-05 | SCRUM-8 | Create the Folder Structure in the Implementation folder | 1 | Sprint 2 - Set Up the Backend