## Jira Export Excel CSV (filter f
Date Worked On | Summary | Sprint | Issue key | Custom field (Story point estimate) | Status
2025-04-05 | Progress Report #5 | Sprint 8 - UI and Final Report | SCRUM-65 | 1.5 | Done
2025-04-05 | Personalize Feature for additional novelty Day 4 | Sprint 8 - UI and Final Report | SCRUM-64 | 2 | Done
2025-04-04 | Personalize Feature for additional novelty Day 3 | Sprint 8 - UI and Final Report | SCRUM-63 | 2.5 | Done
2025-04-03 | Personalize Feature for additional novelty Day 2 | Sprint 8 - UI and Final Report | SCRUM-62 | 2.5 | Done
2025-04-02 | Final Report Documentation 1 | Sprint 8 - UI and Final Report | SCRUM-56 | 1 | Done
2025-04-01 | Personalize Feature for additional novelty Day 1 | Sprint 8 - UI and Final Report | SCRUM-61 | 3 | Done
2025-03-30 | Progress Report #4 | Sprint 7 - Auto Email & UI | SCRUM-54 | 1 | Done
2025-03-29 | Title and Abstract | Sprint 8 - UI and Final Report | SCRUM-59 | 1 | Done
2025-03-28 | Retry Production Environment Deployment | Sprint 7 - Auto Email & UI | SCRUM-53 | 6 | Done
2025-03-26 | UI Enhancement 2 | Sprint 7 - Auto Email & UI | SCRUM-58 | 1.5 | Done
2025-03-26 | Store Frequently Asked Questions in MongoDB | Sprint 7 - Auto Email & UI | SCRUM-29 | 3 | Done
2025-03-25 | UI Enhancement 1 | Sprint 7 - Auto Email & UI | SCRUM-55 | 4 | Done
2025-03-24 | Automate Email Reminders | Sprint 7 - Auto Email & UI | SCRUM-52 | 2 | Done
2025-03-18 | Deploy FurBot to Railway 3 | Sprint 6 - Prod Deployment | SCRUM-49 | 6 | Done
2025-03-17 | Deploy FurBot to Railway 2 | Sprint 6 - Prod Deployment | SCRUM-48 | 4 | Done
2025-03-12 | Test and Debug - March 12 | Sprint 6 - Prod Deployment | SCRUM-47 | 4 | Done
2025-03-12 | Deploy FurBot to Railway 1 | Sprint 6 - Prod Deployment | SCRUM-46 | 4 | Done
2025-03-11 | Sign up with Railway | Sprint 6 - Prod Deployment | SCRUM-45 | 2 | Done
2025-03-10 | Creating Progress Report #2 | Sprint 5 - Chatbot Integration | SCRUM-44 | 2 | Done
2025-03-06 | Integrate Yelp with Backend API - March 6 | Sprint 5 - Chatbot Integration | SCRUM-40 | 1 | Done
2025-03-06 | Integrate Yelp with Chatbot UI - March 6 | Sprint 5 - Chatbot Integration | SCRUM-39 | 1 | Done
2025-03-05 | Integrate Yelp with Backend API - March 5 | Sprint 5 - Chatbot Integration | SCRUM-38 | 1 | Done
2025-03-05 | Integrate Yelp with Chatbot UI - March 5 | Sprint 5 - Chatbot Integration | SCRUM-37 | 2 | Done
2025-03-05 | Implement Basic Conversation Flow | Sprint 5 - Chatbot Integration | SCRUM-32 | 1 | Done
2025-03-04 | Integrate Yelp with Chatbot UI - March 4 | Sprint 5 - Chatbot Integration | SCRUM-36 | 2 | Done
2025-03-04 | Integrate Yelp with Backend API - March 4 | Sprint 5 - Chatbot Integration | SCRUM-35 | 2 | Done
2025-03-04 | Create initial Chatbot UI | Sprint 5 - Chatbot Integration | SCRUM-30 | 1 | Done
2025-03-04 | Yelp Registration and Initial Set up | Sprint 5 - Chatbot Integration | SCRUM-28 | 1 | Done
2025-03-03 | Integrate Yelp with Chatbot UI - March 3 | Sprint 5 - Chatbot Integration | SCRUM-34 | 1 | Done
2025-03-03 | Integrate Yelp with Backend API - March 3 | Sprint 5 - Chatbot Integration | SCRUM-31 | 1 | Done
2025-02-26 | Implement Basic Chatbot Logic | Sprint 5 - Chatbot Integration | SCRUM-27 | 5 | Done
2025-02-20 | Midterm Report and Video | Sprint 5 - Chatbot Integration | SCRUM-33 | 5 | Done
2025-02-19 | Create API Endpoint for Chatbot (/chatbot) and Simple UI Integration | Sprint 5 - Chatbot Integration | SCRUM-26 | 5 | Done
2025-02-18 | UI testing & debugging | Sprint 4 - Building Initial UI | SCRUM-25 | 6 | Done
2025-02-18 | API integration for authentication & pet management | Sprint 4 - Building Initial UI | SCRUM-23 | 3 | Done
2025-02-17 | User session handling (store token & authentication state) | Sprint 4 - Building Initial UI | SCRUM-24 | 4 | Done
2025-02-17 | Basic UI for Adding & Viewing Pets | Sprint 4 - Building Initial UI | SCRUM-22 | 2 | Done
2025-02-17 | Functional UI for Login & Sign-Up | Sprint 4 - Building Initial UI | SCRUM-21 | 2 | Done
2025-02-11 | Set up Job Scheduler to automate the email reminders | Sprint 3 - Backend Setup | SCRUM-20 | 3 | Done
2025-02-09 | Set up Reminders | Sprint 3 - Backend Setup | SCRUM-17 | 3 | Done
2025-02-09 | Create end points for pet profiles | Sprint 3 - Backend Setup | SCRUM-16 | 2 | Done
2025-02-09 | Set up MongoDB for Pet Profiles | Sprint 3 - Backend Setup | SCRUM-15 | 1 | Done
2025-02-06 | Progress Report #1 | Sprint 4 - Building Initial UI | SCRUM-18 | 2 | Done
2025-02-06 | Test API | Sprint 2 - Set Up the Backend | SCRUM-14 | 1 | Done
2025-02-06 | Build User Authentication API | Sprint 2 - Set Up the Backend | SCRUM-12 | 3 | Done
2025-02-05 | Set Up MongoDB | Sprint 2 - Set Up the Backend | SCRUM-11 | 1 | Done
2025-02-05 | Install Dependencies | Sprint 2 - Set Up the Backend | SCRUM-10 | 1 | Done
2025-02-05 | Set Up Python and Virtual Environment | Sprint 2 - Set Up the Backend | SCRUM-9 | 1 | Done
2025-02-05 | Create the Folder Structure in the Implementation folder | Sprint 2 - Set Up the Backend | SCRUM-8 | 1 | Done
2025-01-25 | Draft Project Proposal | Sprint 1 - FurBot Setup | SCRUM-1 | 6 | Done
2025-01-19 | Set Up Project Repository | Sprint 1 - FurBot Setup | SCRUM-6 | 1 | Done
2025-01-19 | Set Up JIRA for Project Management | Sprint 1 - FurBot Setup | SCRUM-2 | 2 | Done
2025-01-18 | Research a topic for the project proposal | Sprint 1 - FurBot Setup | SCRUM-13 | 2 | Done
2025-01-18 | Research and Identify Technologies for FurBot | Sprint 1 - FurBot Setup | SCRUM-7 | 2 | Done
| Implementation |  | SCRUM-5 |  | Done

## Sheet1
Date Worked On | Summary | Issue key | Hours Log | Status
2025-03-29 | Title and Abstract | SCRUM-59 | 1 | Done
2025-04-01 | Personalization Feature for Added Novelty – Day 1 - Created the API route for proactive reminders. For the MVP, it only checks for appointment types grooming and vaccination > For grooming it will check the last reminder set for grooming and if it is (>30 days), the system will send a reminder email that the pet is due for grooming. > For vaccination with the same implementation with (>365 days) from the last vaccination reminder. | SCRUM-61 | 3 | Done
2025-04-02 | Final Report Documentation 1 - Introduction - Introducing the domain, and overview of the background, and context of the research - Problem Statement - Relevant Literature and Research - Hypothesis, Assumptions, and Potential Benefit of Research - Summary of the research project | SCRUM-56 | 1 | Done
2025-04-03 | Personalize Feature for additional novelty - Day 2 - Created the API for favorites from Yelp results - POST - GET - DELETE - Created a new favorites collection in MongoDB to store items marked as favorites by users. | SCRUM-62 | 2.5 | Done
2025-04-04 | Personalize Feature for additional novelty - Day 3 - Created FavoriteList.vue | SCRUM-63 | 2.5 | Done
2025-04-05 | Progress Report #5 | SCRUM-65 | 1.5 | Done
2025-04-05 | Personalize Feature for additional novelty Day 4 - Updated the Dashboard.vue to add the Favorites.vue to the dashboard. | SCRUM-64 | 2 | Done